## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Team D SuperAlphaGo: Justin Yau, Brian Mirabito, Kyle McCoy, Luyang Lin
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass |  | LL 10/09/2019
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass |  | LL 10/09/2019
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass |  | LL 10/09/2019
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass |  | LL 10/09/2019.
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass |  | LL 10/09/2019
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass |  | LL 10/09/2019
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass |  | LL 10/09/2019
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass |  | LL 10/09/2019
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass |  | LL 10/09/2019
| Given that a player is already in a game when I view the player lobby then I will not see that player listed as they are unavailable to play a game. | Pass |  | LL 10/09/2019
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass |  | LL 10/09/2019
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass |  | LL 10/09/2019
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass |  | LL 10/09/2019
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass |  | LL 10/09/2019
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass |  | LL 10/09/2019
As a Player, I want the system to determine and notify players whose turn it is so that we don’t have to keep track of it. | **Given** I am playing a checkers game and on the game view **when** I am waiting for my turn and my opponent resigns **then** I expect to receive a notification notifying me of the event. |  | Pass | JY 11/05/2019
| **Given** I am playing a checkers game and on the game view **when** I am waiting for my turn and my opponent resigns **then** I expect to have a means to sign-out or go back to the homepage. |  | Pass | JY 11/05/2019
| **Given** I am playing a checkers game and on the game view **when** I am waiting for my turn and my opponent makes their turn **then** I expect to receive a notification notifying me of the event. |  | Pass | JY 11/05/2019
| **Given** I am playing a checkers game and on the game view **when** I am waiting for my turn and my opponent makes their turn **then** I expect to be able to make my move. |  | Pass | JY 11/05/2019
As a Player, I want to be able to resign from the game. | **Given** I am playing a checkers game and on the game view **when** it's my turn and I have not made a move yet **then** I expect to see a means to resign. |  | Pass | JY 11/05/2019
| **Given** I am playing a checkers game and on the game view **when** it's my turn and I have made a move without reversing it **then** I expect to not see a means to resign. |  | Pass | JY 11/05/2019
| **Given** I am playing a checkers game and on the game view **when** it's my turn and I have made a move but undid it **then** I expect to see a means to resign. |  | Pass | JY 11/05/2019
| **Given** I am playing a checkers game and on the game view **when** I am waiting for my turn **then** I expect to see a means to resign. |  | Pass | JY 11/05/2019
| **Given** I am playing a checkers game and on the game view **when** I attempt to resign **then** I expect to see a confirmation alert. |  | Pass | JY 11/05/2019
| **Given** I received the resignation confirmation alert **when** I confirm **then** I expect to be redirected back to the homepage. |  | Pass | JY 11/05/2019
| **Given** I received the resignation confirmation alert **when** I cancel **then** I expect to be notified of my attempt and be able to continue my game. |  | Pass | JY 11/05/2019
As a Player, I want to let the system determine if there is a winner so that me and my opponent don’t have to check at the end of each turn. | **Given** I am playing a checkers game **when** I make a winning move **then** I expect to be prompted with a win notification and a means to exit the game. |  | Pass | JY 11/05/2019
| **Given** I am playing a checkers game **when** my opponent makes a winning move **then** I expect to be prompted with a lose notification and a means to exit the game |  | Pass | JY 11/05/2019
As a Player, I want to be able to reset my move so I can make a different move or correct an invalid move. | Given I am playing a checkers game and it's my turn when I make an invalid move then I expect to be able to reset my move by pressing a button. |  | Pass | BM 11/05/2019
| Given I am playing a checkers game and it's my turn when I press the reset button then I expect my pieces to move back to their last valid place. |  | Pass | BM 11/05/2019
As a Player, I want to be able to submit my turn when I am ready to do so. | **Given** A player **when** they complete their turn **then** they are able to click the submit button. |  | Pass | BM 11/05/2019
| **Given** The game **when** the game state is in `stable` **then** the submit button will be able to be clicked. |  | Pass | BM 11/05/2019
| **Given** A user takes a single move turn **when** user has a jump turn somewhere else **then** that single move is not a valid turn and an `ERROR` message is returned saying that there is a jump move somewhere else. |  | Pass | BM 11/05/2019
| **Given** A player clicks the submit button **when** that turn is legal and valid **then** a message with type `INFO` is sent and the game view updates. |  | Pass | BM 11/05/2019
As a Player I want to be notified when I have to jump so that I can make a valid move. | Given I am playing a checkers game, it's my turn, and a jump is available when I make a move that isn't a jump then I expect to receive a notification telling me to make the jump. |  | Pass | KM 11/05/2019
| Given I am playing a checkers game, it's my turn, I've already made a jump, but another jump is available when I submit my move then I expect to receive a notification telling me to make another jump move. |  | Pass | KM 11/05/2019
As I player, I want to be forced to complete a multiple-jump-move once it is started so I can be confident that I am playing by the rules | **Given** when it is my turn playing a checkers game **When** I moved one of my pieces into a multiple-jump-move **then** I expect to be forced to complete the move sequence. |  | Pass | KM 11/05/2019
| **Given** when it is my turn playing a checkers game **When** I moved one of my pieces into a multiple-jump-move **then** I expect to be informed on the GUI that I just initiated such move and be able to see its movement path from the start to end |  | Pass | KM 11/05/2019
As a Player, I want to be able to tell which pieces are kings and which aren’t. | **Given** One of my pieces **when** crosses to the other side of the board **then** the piece has an icon appear on it showing that it is a king. |  | Pass | KM 11/05/2019
As a Player, I want the system to notify me if I made an illegal move and undo it so that I could make a legal move. | **Given** I am playing a checkers game and it's my turn **when** I make an illegal move **then** I expect to receive a notification telling me to make another move. |  | Pass | KM 11/05/2019
| **Given** I am playing a checkers game and it's my turn **when** I am notified that I made an illegal move **then** I expect to be able to make another move . |  | Pass | KM 11/05/2019
As a player I want to be able to spectate a game when there is an active game being played. | **Given** I want to spectate a game and am logged in **when** I view the home screen **then** I want to see a list of games that I can spectate. |  | Pass | JY 11/14/2019
| **Given** I want to spectate a game and am logged in **when** I click spectate game **then** I expect to join the game as a spectator. |  | Pass | JY 11/14/2019
| **Given** I am spectating **when** I wait a short amount of time **then** I expect to have the latest state of the game. |  | Pass | JY 11/14/2019
| **Given** I am spectating a game **when** the game ends **then** I expect to be notified of the result with a means to exit. |  | Pass | JY 11/14/2019
As a player spectating a game I want to be able to stop spectating at any point. | **Given** I am spectating a game **when** I want to stop spectating **then** I expect to see a stop spectating button. |  | Pass | JY 11/14/2019
| **Given** I am spectating a game **when** I click the stop spectating button **then** I expect to be automatically brought back to the home screen. |  | Pass | JY 11/14/2019
| **Given** I am spectating a game **when** I stop spectating **then** I expect to be able to start spectating again or play a game. |  | Pass | JY 11/14/2019
| **Given** I am spectating a game **when** I sign out **then** I expect to be able to sign in again. |  | Pass | JY 11/14/2019
| **Given** I am spectating a game **when** I sign out **then** I expect my username to be freed and the server to cleanup any states that I was in. |  | Pass | JY 11/14/2019
As a player at the game view I want to be able to click a "get help" button that will give me helpful info through an overlay. | **Given** I am playing a checkers game **when** I would like to request help **then** I expect a help button that I could press to do so. |  | Pass | LL 11/21/2019
| **Given** I am playing a checkers game **when** I request help **then** I expect the system to give me information through an overlay. |  | Pass | LL 11/21/2019
| **Given** I am playing a checkers game **when** I view the help overlay **then** I expect useful information to help me make more informed moves. |  | Pass | LL 11/21/2019
As a player with the get help overlay open, I want to be able to close the overlay. | **Given** I have the help overlay open **when** I click outside of the overlay**then** I expect the overlay to close. |  | Pass | LL 11/21/2019
| **Given** I have the help overlay open **when** I click the X button in the top corning of the overlay, ** then** the overlay will close. |  | Pass | LL 11/21/2019